## Sheet1
S.No | Project Name | Project Executive | Project Manager | Start Date | End Date | Status | Aging | No of resources | Efforts in hours | Skipped count | Revised End Date | Remarks
1 | Samplig | Pilla Manisha | Matturti Eshwar | 2023-10-26 | 2023-11-16 | Ready for UAT | 106 | 3 | 3000 | 4 | 2024-02-20
2 | AR Automation Phase -1 | Ajay Bali | Raghumanda Chandrakala | 2024-01-25 | 2024-01-31 | Ready for UAT | 15 | 2(1shared) | 76 | 1 | 2024-02-12 | live completed for 1(Decthlon) plant remaining 2(H&M, Uniqlo) waiting on client for logistic invoices
3 | Trading Software | Reddi Bhanuteja | Raghumanda Chandrakala | 2022-05-01 | 2023-04-15 | Work in progress | 649 | 3(1shared) | 1540 | 6 | 2024-03-20 | -->on 12th Application will be moved to production -->it will take approximately one month for Data migration as our developers need to go to the client location --> Note:- efforts are considered from oct-2023 (project handover date to Chandrakala)
4 | Xapparel | Reddi Bhanuteja | Gorja Sandeep | 2023-06-29 | 2023-07-31 | Work in progress | 225 | 8(5 Shared) | 393 | 2 | 2024-02-25
5 | 8-Buyer OMS & BOT | Katiki Sai Prakash | Matturti Eshwar | 2023-12-06 | 2024-02-16 | Work in progress | 65 | 3 | 1050 | 1 | 2024-02-25
6 | Auto PO approval | Raghumajji Dileep Kumar | Gorja Sandeep | 2023-12-20 | 2024-01-08 | Ready for UAT | 51 | 2 | 381 | 2 | 2024-01-12 | All the changes have been completed, Bidhun will perform UAT and confirm by Monday
7 | Sampling PO automation | Katiki Sai Prakash | Gorja Sandeep | 2024-02-03 | 2024-02-05 | Ready for UAT | 6 | 2 | 60 | 1 | 2024-01-12 | New CR's suggested by Bidhun Need official confirmation
Formulas:
Aging = TODAY()-[Start Date]